## Read me
#VALUE! | Workplace Risk Register Template (NZ)
How to use | 1. Go to the 'Risk register' tab. 2. Delete the yellow example row (EX-1) when you are ready. 3. Add one row per risk. 4. Score likelihood and consequence (1–5) using the 'Scoring' tab. 5. Add controls, an owner and a due date for every risk rated High or Extreme.
Cells you edit | Pale yellow cells are inputs. Grey cells (score, rating, next review) calculate automatically – do not overwrite them.
Scoring | Score = Likelihood x Consequence (1–25). The rating bands are on the 'Scoring' tab and can be changed in the yellow cells there.
Critical risks | Mark 'Y' in the Critical risk column for risks that could cause death or serious harm. These should get the most attention and the strongest controls.
Inherent vs residual | Inherent = the risk with no controls. Residual = the risk after your controls and actions are in place. Re-score residual risk honestly after controls are implemented.
Summary | The 'Summary' tab counts risks by rating and flags overdue actions.
Review | Enter the date you last reviewed each risk. Next review date is calculated using the review interval on the 'Scoring' tab (default 3 months).
Capacity | The register has room for 50 risks (rows 5–54). To add more, copy the last row down and extend the ranges on the Summary tab.
Important | This is a general template, not legal advice. It does not replace consultation with your workers, or advice specific to your workplace and industry. Under the Health and Safety at Work Act 2015 a PCBU must manage risks so far as is reasonably practicable.

## Risk register
Risk register | [19 empty] | #VALUE!
Yellow = you fill in. Grey = calculates automatically. Row 5 is an example (EX-1): overwrite or delete it.
ID | Area / activity | Hazard | What could happen | Who could be harmed | Critical risk? (Y/N) | Existing controls | Likelihood (1–5) | Consequence (1–5) | Inherent score | Inherent rating | Additional controls / actions | Action owner | Due date | Residual likelihood (1–5) | Residual consequence (1–5) | Residual score | Residual rating | Status | Last reviewed | Next review
EX-1 | Warehouse – loading dock | Forklifts operating near pedestrians | Pedestrian struck by forklift causing serious injury or death | Warehouse staff, drivers, visitors | Y | Marked walkways; speed limit on site; licensed operators | 2 | 5 | 10 | High | Physical barriers at dock doors; pedestrian exclusion zone during loading; review traffic management plan | Operations Manager | 2026-11-30 | 2 | 5 | 10 | High | In progress | 2026-09-21 | 2026-12-21
Formulas:
Next review = IF([Last reviewed]="","",EDATE([Last reviewed],Scoring!$C28))

## Summary
#VALUE!
Risk summary
Rating | Inherent | Residual
Extreme | 0 | 0
High | 1 | 1
Medium | 0 | 0
Low | 0 | 0
Total risks | 1 | 1
Critical risks (marked Y) | 1
Actions not yet closed | 1
Overdue actions | 0
Reviews overdue | 0
Note: the example row (EX-1) is included in these counts until you delete it.

## Scoring
Scoring guide
Likelihood (how likely is harm to occur?)
Score | Label | Guide
1 | Rare | Could happen but only in exceptional circumstances
2 | Unlikely | Could happen at some time, but not expected
3 | Possible | Might happen at some time – has occurred in similar workplaces
4 | Likely | Will probably happen in most circumstances / has happened here
5 | Almost certain | Expected to happen regularly
Consequence (how bad would the harm be?)
Score | Label | Guide
1 | Insignificant | No injury or first aid only
2 | Minor | Minor injury needing medical treatment; short time off work
3 | Moderate | Injury or illness needing hospital treatment; lost time
4 | Major | Serious harm – e.g. permanent impairment or long-term illness
5 | Catastrophic | Death, or multiple serious injuries
Rating bands (edit yellow cells if your policy differs)
Rating | Minimum score | What to do
Low | 1 | Monitor. Manage through routine procedures.
Medium | 4 | Manage with additional controls where reasonably practicable. Assign an owner.
High | 10 | Senior attention needed. Action plan with owner and due date.
Extreme | 15 | Do not start / continue the activity until controls reduce the risk. Escalate to leadership.
Review interval (months) | 3 | Assumption: risks are reviewed every 3 months. Change to suit your workplace.

## Hazard prompts
Hazard prompts – to get you started
Not exhaustive. Walk your site, talk to your workers, and add what applies to your workplace.
Workplace type | Common hazards to consider
Warehouse / logistics | Forklift and pedestrian interaction; racking damage or overload; falling objects; manual handling; loading dock falls; vehicle movements in yard; hazardous goods storage
Manufacturing | Machine guarding; lockout / tagout; noise; dust and fumes; hot work; hazardous substances; manual handling; slips and trips
Construction / contractors | Work at height; excavation; plant and vehicles; electrical; asbestos; contractor competence and coordination; site traffic
Office / retail | Manual handling; slips and trips; aggression or abuse from the public; lone working; psychosocial harm (stress, workload, bullying); fire and evacuation
Any workplace | Hazardous substances; electrical safety; driving for work; fatigue; emergency response; contractors and visitors; new or changed equipment or processes